| TO: | Harvard Growth Lab Administration |
| --- | --- |
| FROM: | Andrés Fortunato and Claude |
| DATE: | May 1, 2026 |
| RE: | Piloting Claude with the Córdoba and Cambodia Applied Research Teams |

# Executive summary

Applied economists are increasingly using Claude and Claude Code to accelerate research workflows, raise quality and consistency, and build new types of products that were previously out of reach. This memo requests approval to pilot these tools with the Growth Lab's Córdoba and Cambodia engagements through August and September 2026 respectively, and lays out the rationale, scope, deliverables, procurement plan, and evaluation methodology.

Through this pilot, we want the Growth Lab's applied research team not only to catch up with current research tools, but also to become a leader in using AI for applied economic development research, open-sourcing tools and sharing workflows with the world.

The document describes what Claude and Claude Code are (Section 1); introduces use cases of two categories: a- existing workflows the pilot will accelerate, and b- aspirational new products the pilot will explore (Section 2), along with its risks and planned guardrails; what the intended benefits are (Section 3)) what are expected public goods from this pilot in terms of workflows, skills, and tools (Section 4); identifies planned deliverables (Section 5), describe the recommended subscription type and how it works (Section 6); establishes what responsible use looks like (Section 7), and shares a timeline and evaluation design (Section 8)

# Introduction: What Claude and Claude Code are

For readers less familiar with the tools:

Claude is a conversational AI assistant similar in form to ChatGPT, accessed through a web app or a phone app. Researchers chat with it, upload documents, ask questions, and have it generate text, summaries, code, or analysis. It can browse the web and connect to third-party data sources through "connectors" (for example, Google Drive, Notion, or specialized research databases).

Claude Code is Anthropic's agentic coding tool. Rather than just chatting back and forth, Claude Code runs on the researcher's own computer, where it can read and write files, execute code, run analyses, fetch data from external APIs, and complete multi-step research tasks under the researcher's supervision. The researcher reviews intermediate outputs and approves changes at each step. Claude Code is the right tool for substantive applied-research workflows: anything that involves running scripts, building data pipelines, or processing many files at once.

Anthropic's Team plan bundles both products. Premium seats include Claude Code; Standard seats include Claude alone, with optional metered access to Claude Code through extra usage (described in detail in the Plan recommendation section).

# Use cases

We organize use cases into two categories. Category 1 covers doing existing work faster, applying Claude across the workflow we already have. Category 2 covers doing things we previously could not do at all, or could do only with substantially more effort and budget than was justifiable. Category 1 use cases will be exercised continuously throughout the pilot. Category 2 use cases are aspirational targets that we expect to explore selectively as time and counterpart needs allow; they are not committed deliverables of the pilot. This list is illustrative, not exhaustive.

For each use case we identify the risks (what can go wrong if the tool is used carelessly) and the guardrails (procedures we will adopt to mitigate those risks). The guardrails complement, but do not replace, the cross-cutting principles in the Responsible use section below.

## Category 1: Doing current work faster

| Use case | Description | Risks | Guardrails |
| --- | --- | --- | --- |
| Writing and editing | Most of our researchers work in a second or third language. Claude corrects grammar, improves style, and restructures memos, briefs, dissemination pieces, and slide-deck narrative. | Loss of authorial voice; "fluent" rephrasing introducing factual drift; uncritical acceptance of substantive edits; passing AI-generated prose as one's own thinking. | Treat Claude as a copyeditor, not a co-author; review every changed sentence; never accept rewrites of substantive claims without verifying against the underlying source. |
| Discovery: corpus analysis and stakeholder role-prompting | Upload a country's policy corpus and prior diagnostics and interrogate them: ask focused questions, surface relevant passages, identify cross-document inconsistencies. Complemented by role-prompting (asking Claude to take on stakeholder perspectives, such as a manufacturing investor, a real estate developer, or a finance ministry official) to map the question space during research. | Hallucinated content or quotes; over-reliance on summaries instead of reading actual passages; treating role-played stakeholder views as evidence rather than ideation. | Require Claude to cite back to source documents; spot-check 10 to 20 percent of claims against originals; treat role-prompting outputs as hypothesis-generation only, never as substitutes for real interviews. |
| Data acquisition: public APIs and MCP servers | Claude Code connects directly to data sources, including the World Bank Data360 MCP server, IMF SDMX APIs, FRED, BLS, BEA, and ECB, pulls relevant indicators, and assembles clean panels. Replaces source-specific custom scripting. | Wrong indicator pulled; freshness mismatched across sources; unit, scale, or vintage quirks not caught (for example, real versus nominal, base year confusion). | Researcher specifies indicator codes explicitly; Claude documents what it pulled, from where, and on what date; cross-check at least one series against a known reference value before use. |
| Data analysis: descriptives, pipelines, and econometrics | The full empirical workflow, from first-look descriptives (Goldsmith-Pinkham 2026) through panel construction, model estimation (DiD, RDD, event studies), and figure production. Claude Code executes the steps; the researcher reviews intermediate outputs at each stage. Doing the Córdoba spatial-equilibrium analysis (web scraping listings, cleaning, merging wage and employment data, estimating the model) is an example from a GL applied project. | Code that runs but does the wrong thing; subtle specification errors (wrong fixed effects, mis-specified clusters); intermediate outputs not reviewed; black-box analysis the researcher cannot defend. | Plan-first protocol (write the analytical plan, then execute step by step); review intermediate outputs at every stage; require commented, readable code; version-control everything; pin dependencies. |
| Bulk document processing | Extracting tables from scanned PDFs, classifying corpora of news articles, comparing many versions of a draft regulation. Tasks that scale by file count and are well-suited to programmatic iteration. | Silent processing or sampling errors at scale; misclassification not caught because no human read the inputs. | Manual audit of a random sample of outputs; explicit classification rubrics; second-pass review by a different team member for high-stakes outputs. |
| Literature review and replication of related work | A growing community of academic economists has published reusable Claude Code "skills" for structured paper review, replication-package audits, and pre-submission referee reports (Crawfurd 2025; Cunningham 2026; Sant'Anna 2025). For our purposes: replicating others' published work that bears on our engagements (for instance, a key Argentina-on-Argentina paper) and verifying its findings hold under independent execution. | Missing key citations; misrepresenting authors' findings; replication failures attributed wrongly (was it the original or our re-execution that broke); over-trusting Claude's reading of papers. | Researcher reads abstract and key sections of every cited work; replication anomalies flagged for human investigation before any conclusion is drawn; never use Claude as the sole basis for citing a paper. |
| Internal newsletters and recurring briefs | Recurring written products for the internal research team. Lucas's Córdoba newsletter is the model. The researcher defines data sources and an editorial template once; each issue then involves pulling fresh articles through web search. | Irrelevant data slipping through; tone drift over time; uncritical reproduction of past framing as the world changes. | Editorial sign-off before each issue; data-freshness checks built into the pipeline; periodic editorial review of the template itself. |
| Dashboards and digital research products | The Viz Hub remains the institutional flagship, but bespoke per-engagement dashboards (imagine a Córdoba labor-market tracker for the provincial government, or a Cambodian SEZ monitor for the Council for the Development of Cambodia) were previously priced out. With Claude Code, a single applied researcher can prototype a publication-quality interactive dashboard in days. | Visualization errors that mislead (truncated axes, non-colorblind palettes); technical debt as researcher-built tools accumulate without maintenance; tools shipped without source attribution. | Design checklist (zero baselines for bars, colorblind-safe palettes, source attribution on every chart); shared component library; explicit ownership and maintenance commitment for any tool that goes to a counterpart. |

## Category 2: Doing things we previously could not do (aspirational)

| Use case | Description | Risks | Guardrails |
| --- | --- | --- | --- |
| Counterpart-facing research chatbots and "diagnostic-as-conversation" | A retrieval-augmented (RAG) chatbot indexed on our final research outputs that lets a counterpart, such as a civil servant in Córdoba or a director at the Council for the Development of Cambodia, ask grounded questions and get answers cited back to specific reports and pages. The longer-form version is diagnostic-as-conversation: an interactive product (chat plus dashboards) that walks a policymaker through their country's growth diagnostic, surfacing evidence on demand. A strategic question worth surfacing is whether productizing the diagnostic this way complements or partly cannibalizes the Lab's bespoke-consulting model. | Hallucinated answers attributed to the Growth Lab; outdated content delivered with confidence; chatbot replacing direct relationships rather than augmenting them; counterparts misinterpreting nuance. | Strict citation discipline (every answer linked to source paragraphs); only curated final outputs in the corpus, never drafts; explicit "verify with the team" disclaimer; quarterly content refresh; usage analytics reviewed regularly. |
| Bespoke research datasets at scale | Building original datasets that did not exist before, by combining bulk document processing and web scraping at a scale that was previously prohibitive. The Global Industrial Policy Database (industrialpolicydata.com) is the model: a structured panel of policy interventions assembled from thousands of unstructured government documents, news sources, and trade publications, now used widely in the innovation and trade literatures. Similar datasets are now within reach across our research areas, from housing supply regulation to FDI incentive regimes to subnational productive capabilities. These datasets can become standalone Growth Lab outputs in their own right, complementing our diagnostic and country reports. | Coding errors at scale that bias the resulting dataset systematically; opaque source attribution that limits external use; inconsistent definitions across documents masquerading as comparable observations; over-reliance on the dataset as evidence when its construction is itself contestable. | Pre-registered coding rubrics with worked examples; manual gold-standard sample (target: 5 percent of observations) to measure accuracy and inter-coder agreement against the AI labels; full provenance for every observation (source URL, document, paragraph); public release of construction code alongside the dataset; prominent documentation of definitional choices and known limitations. |
| Tailored educational content for state capacity building | Workshops and short courses, built per engagement, that walk policymakers through the methods and findings of their own engagement rather than generic textbook material. Includes exercises against their actual data, simulations grounded in their context, and slides and lecture notes in the local language. | Plausible-sounding but wrong material reaching learners; difficulty calibration off; cultural or contextual mismatches; over-reliance on generated material without senior researcher review. | Researcher reviews of all material before use; pilot with a small cohort first; structured feedback loop after every workshop; native-speaker review of language-localized content. |
| Synthetic stakeholder consultations | Pre-engagement structured exercises that simulate a multi-stakeholder consultation (a manufacturer, an exporter, an SME owner, a labor leader, a finance ministry official) on a draft policy proposal, with each persona grounded in actual interviews and documents from prior engagements. Used to stress-test framing and identify objections before the real consultation. | Treating simulated views as real evidence; missing real stakeholders' actual concerns; false confidence about how a proposal will land. | Never substitute for real consultation; explicit "stress-test only" framing on every output; debrief after every real consultation comparing simulated to actual responses. |
| Continuous policy monitoring agents | A long-running agent that ingests official bulletins, central bank releases, news, and parliamentary records from the engagement country, summarizes what is relevant to the diagnostic, and alerts the team. Replaces the current default ("someone has to remember to check") that mostly does not happen. | Missing important signals; alert fatigue from false positives; misclassification of politically charged content; legal exposure if alerts are mistaken for advice. | Human review of every alert before it triggers action; weekly calibration of relevance rules; clear internal-use-only framing on outputs. |
| Multilingual research dissemination at industrial scale | Auto-generate Spanish, Khmer, French, and Portuguese versions of every report, brief, and social post, with researcher review of technical terminology. Translation cost and time, currently the bottleneck on dissemination, mostly disappear. | Translation errors in technical terms (for example, the specialized vocabulary of growth diagnostics); loss of nuance in policy recommendations; cultural mismatches in framing. | Native-speaker review for technical accuracy on every output; standard glossary maintained per language; localization style guide. |
| Co-built tools with counterpart data teams | Instead of the Lab building a tool and handing it over, the team works alongside local government data teams to co-build their version of an analytical tool, with Claude Code as the substrate. The deliverable shifts from "a report and a dashboard" to "a report, a dashboard, and a local team that can extend it." | Counterpart team does not actually adopt; tools become abandonware after the engagement closes; unclear data governance and security responsibilities. | Co-development from day one rather than handover at the end; explicit maintenance commitment from the counterpart; documented data-governance roles; design decisions logged in a shared repository. |
| The "Roast Me" agent | A specialized public agent whose only job is to attack a Growth Lab draft from the perspectives of a skeptical economist, a fiscally constrained finance minister, an academic referee, and an opposition critic. Output is a structured, prioritized list of weaknesses. The agent is public within the Lab: every roast is visible to the team, so no researcher can quietly run it and pass its feedback off as their own thinking. | Researchers demoralized or avoiding the tool; over-tuning drafts to AI critique at the expense of substance; missing real critical issues; treating the roast as a substitute for human peer review. | Public visibility of every roast; calibrated severity (the agent flags severity tiers, the researcher decides response); explicitly framed as complement to, not substitute for, internal peer review. |

# Intended benefits

The benefits we expect are now documented in a substantial empirical literature on LLM-assisted research:

- Faster onboarding to new contexts. For Córdoba and Cambodia, where researchers must rapidly absorb unfamiliar policy environments, the document-interrogation and role-prompting use cases compress weeks of background reading into days.

- A reusable internal playbook. The pilot will produce documented prompts, workflows, and quality-control checklists that other Growth Lab teams can adopt without repeating the learning curve.

- Productivity. Korinek (2023, 2024) catalogues 25+ research use cases across ideation, writing, background research, data analysis, coding, and mathematical derivations, and argues that economists who automate these micro-tasks become significantly more productive. Merali (2024, 2025), in pre-registered experiments with hundreds of professional knowledge workers, finds that successive generations of AI models reduce task time by roughly 8 percent per year, with substantially larger gains for less-experienced workers.

- Quality and consistency. A 2026 replication of the well-known "many analysts, one dataset" study (originally Huntington-Klein et al. 2021) found that agentic AI systems produced conclusions near the human-economist median but with much tighter dispersion and no extreme outliers, suggesting genuine reproducibility gains for exploratory analysis. Cunningham (2026) and Sant'Anna (2025) emphasize a complementary point: Claude Code's value is partly in enforcing checklists (consistent SE clustering, source attribution on every figure, replicable directory structures) that researchers know they should follow but rarely do under deadline.

# Public goods commitment

A small but rapidly developing community of academic economists is already publishing reusable Claude Code "skills" (templated prompts that run as slash commands like /audit-reproducibility) and "agents" (specialized sub-Claudes such as a code auditor or regression checker). Active contributors as of early 2026 include Scott Cunningham (Baylor, MixtapeTools, with regular dispatches on his Causal Inference Substack), Pedro Sant'Anna and Hugo Sant'Anna (paper-centric workflow templates with parallel sub-agents for review), Chris Blattman (UChicago, non-developer-friendly patterns), and Lant Crawfurd (CGD, the aggregator skills repository this memo cites). As of March 2026, roughly 15 research groups across economics, energy, political science, and engineering had forked Sant'Anna's template.

This community is currently dominated by U.S. academic economists working on theoretical and empirical research. Applied development research, including diagnostics, country engagements, and growth strategy, is structurally absent. We see this as both a gap and an opportunity, and we believe the Growth Lab is well-positioned to lead.

Researchers receiving subscriptions through this pilot commit to:

- Documenting the workflows they develop in a shared internal repository, alongside honest accounts of what failed.

- Open-sourcing reusable components (skills, agents, prompt templates) where data and contractual commitments allow.

- Contributing back to the Growth Lab's broader playbook so other teams adopt without repeating the learning curve.

- Where appropriate, publishing outward (blog posts, GitHub repositories, conference talks).

The ambition is not just to use AI for applied research, but to become a recognized contributor to the body of work on how applied development research is done in the AI era.

# Deliverables

The Category 2 use cases above are aspirational targets, not commitments. The pilot itself commits to a small set of concrete deliverables, all of which serve the public-goods commitment and the evaluation plan:

- A documented internal playbook. A shared internal repository of the workflows, prompts, and quality-control checklists developed during the pilot, with honest accounts of what worked and what failed.

- Case studies. Narrative documentation of at least four specific workflows (target: two per engagement) capturing what was tried, what worked, what failed, and what was learned. Andrés Fortunato leads this work, with Claude's assistance, drawing on participant self-reports and interviews.

- Three-checkpoint survey results. A short survey instrument administered before the pilot, mid-pilot, and at close-out, with aggregated findings.

- Public-goods contributions. A target of two to three reusable components (skills, agents, prompt templates) open-sourced, where project commitments allow.

- Initial workshop materials. Slides, demonstration notebooks, and (where possible) a recording from the kickoff workshop, reusable for future onboarding of other Growth Lab teams.

# Plan recommendation: Team, with graduated seat allocation

We recommend the Team plan over Enterprise. Team meets our needs for centralized billing, admin controls, and the data-handling protections we require (Anthropic does not train on Team-plan inputs by default), without the procurement overhead of an Enterprise contract for an early-stage pilot. Team plans support up to 150 seats and allow mixing seat types.

Two seat types are available:

| Seat type | Annual price (USD) | Usage capacity | Includes Claude Code? |
| --- | --- | --- | --- |
| Standard | $20 / seat / month | 1.25× Pro per session | Optional, via extra usage (see below) |
| Premium | $100 / seat / month | 6.25× Pro per session | Yes (included in bundle) |

## Extra usage: pay-per-token after the included allowance

Both seat types can have "extra usage" enabled by the org admin. When a user exhausts the usage allowance bundled into their seat, additional Claude and Claude Code consumption continues at standard API rates rather than being blocked. Critically, this means a Standard seat can access Claude Code on a metered basis, even though Claude Code is not part of the bundled Standard allowance. The admin sets caps to prevent surprise bills: organization-wide caps, per-user monthly caps, or both. Usage is prepaid in credits with optional auto-reload, and the admin dashboard shows month-to-date spend per user.

Per-token rates are identical for both seat types. The price-per-token is the same whether the user holds a Standard or Premium seat; what differs is the included allowance bundled into the seat fee before extra usage kicks in.

| Model | Input ($/Mtok) | Output ($/Mtok) | Notes |
| --- | --- | --- | --- |
| Claude Haiku 4.5 | $1 | $5 | Lightest model; fastest. Suited to high-volume, low-complexity tasks. |
| Claude Sonnet 4.6 | $3 | $15 | Default for most Claude Code work; balanced cost and capability. |
| Claude Opus 4.6 | $5 | $25 | Most capable; reserved for complex reasoning and synthesis. |

A Premium seat includes roughly 5× more bundled usage than a Standard seat, so heavy users come out ahead on Premium because their consumption stays within the bundle. Light or exploratory users come out ahead on Standard plus capped extra usage because they pay only for what they consume. For reference, Anthropic's published Claude Code data shows the average developer spends around $6 per active day at API rates, with 90 percent of users under $12 per active day. A researcher using Claude Code two to three times a week typically falls in the $30 to $70 per month range, well within Standard-plus-cap economics. Daily, multi-hour use pushes past the Premium breakeven.

## Recommended graduated allocation

Rather than guess up front who is a power user, the pilot uses a graduated rollout:

- Premium seats (initial allocation). Reserved for known power users on day one: data-analysis leads on each engagement and the pilot lead.

- Standard seats with capped extra usage (the rest of the cohort). Per-user monthly cap set in the $30 to $50 range. Researchers can experiment with Claude Code through metered access, learn what works for their workflows, and surface their actual usage patterns through the dashboard.

- Graduation rule. If a Standard user consistently approaches their cap, they are upgraded to Premium. The MTD-spend column in the admin dashboard makes this objective and removes the need for self-advocacy.

This design solves a real problem in pilot procurement: we do not have to guess who is a power user before anyone has touched the tools, and the cost of being wrong is bounded. It also has a useful learning effect: Standard-with-cap users see in real time what their experimentation costs, which is itself a kind of training in resource-aware AI use.

# Responsible use

The per-use-case guardrails above operationalize three cross-cutting principles:

- Researcher accountability. All outputs (code, analysis, written products) are reviewed and signed off by the responsible researcher. Claude is a productivity tool, not an author.

- Reproducibility. Recent work (Zhang et al. 2026) has documented dependency-related reproducibility issues in AI-generated code. We pin dependencies, version-control all generated code, and document workflows so any analysis can be re-run.

# Pilot timeline and evaluation

We deliberately move away from a quantitative-first evaluation. Reliable measurement of "hours saved" or "papers produced" against a counterfactual requires baselines we do not have, and the act of measuring would itself distort behavior in costly ways (researchers logging time instead of working, optimizing for measurable rather than meaningful outputs). Instead, we evaluate through a combination of:

- Case studies. Narrative documentation of specific workflows the team developed, with honest accounting of what worked, what did not, and what was learned. Andrés Fortunato leads this work, with Claude's assistance.

- Three-checkpoint surveys. Short surveys (around 15 minutes) administered before the pilot, mid-pilot, and at close-out, with a consistent core block (perceived productivity, perceived quality, blockers, comfort with specific use cases) and open-ended fields where the most useful learning typically lives. Andrés runs the surveys with Claude's assistance for analysis and synthesis.

- Self-evaluation. Participants complete the surveys themselves and contribute brief written reflections to the case studies, capturing individual experience that aggregated synthesis would lose.

- [OPTIONAL] Usage telemetry. The admin dashboard's per-user MTD-spend column provides a lightweight signal of who is engaging with the tools and at what intensity. Used as a diagnostic input alongside the surveys, not as a primary metric.

Timeline:

- May 2026: Approval and procurement. Team-plan setup, seat allocation finalized, accounts provisioned, extra usage enabled with per-user caps configured.

- Mid-May 2026: Initial workshop and pre-pilot survey. A workshop bringing both engagement teams together to demonstrate baseline workflows (Claude chat, Claude Code, MCP connectors), establish shared norms (the public-goods commitment, the responsible-use principles), and capture starting expectations and self-assessed AI fluency in a pre-pilot survey.

- July 2026: Mid-pilot checkpoint. Second survey covering actual use, blockers, and emergent workflows. Each engagement team presents one case study in progress to the other for structured feedback. Initial review of usage telemetry to inform any seat-tier adjustments.

- End of August 2026: Córdoba close-out. Final survey for the Córdoba team, presentation of completed case studies, contribution of reusable components to the shared internal repository.

- End of September 2026: Cambodia close-out and final report. Same close-out structure for the Cambodia team. Report to Growth Lab Administration covering case studies, survey findings, reusable tools produced, and recommended scope of expansion to other Lab teams.

# References

Anthropic. 2025. "Claude Code and new admin controls for business plans." anthropic.com/news/claude-code-on-team-and-enterprise.

Anthropic. 2026. Plans & Pricing. claude.com/pricing.

Anthropic. 2026. Extra Usage for Team and Enterprise Plans (support article). support.claude.com.

Crawfurd, Lant. 2025. Claude Code Skills for Academic Research. lcrawfurd.github.io/claude-skills

Cunningham, Scott. 2026. MixtapeTools: Claude Code workflows for empirical economics. github.com/scunning1975/MixtapeTools. See also Causal Inference: The Mixtape Substack, causalinf.substack.com.

Goldsmith-Pinkham, Paul. 2026. "Data Analysis: Claude Code for Economists." Markus Academy, Princeton.

Huntington-Klein, Nick, et al. 2021. "The Influence of Hidden Researcher Decisions in Applied Microeconomics." Economic Inquiry 59(3): 944–960.

Korinek, Anton. 2023. "Generative AI for Economic Research: Use Cases and Implications for Economists." Journal of Economic Literature 61(4): 1281–1317.

Merali, Ali. 2024. "Scaling Laws for Economic Productivity: Experimental Evidence in LLM-Assisted Translation." arXiv:2409.02391.

Sant'Anna, Pedro H. C. 2025. Claude Code Academic Workflow. psantanna.com/claude-code-my-workflow.

World Bank. 2025. Data360 MCP Server. github.com/worldbank/data360-mcp.

Zhang et al. 2026. "AI-Generated Code Is Not Reproducible (Yet): An Empirical Study of Dependency Gaps in LLM-Based Coding Agents." AAAI 2026. arXiv:2512.22387.